## Aravin
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
19-03-2019 | DISC | Bug fixing | 1 hours | In Progress | - | Forms portal , ISPR | Thenmozhi
| ISPR | Bug fixing | 1 hours | In Progress | -
| iStop | Responsible UI | 1 hours | In Progress | -
| Aatralz | UI issue | 1 hours | In Progress | -
2019-03-20 | Forms portal | Functionality fix | 6.5 hours | In Progress | - | Daimler | Aravin
2019-03-21 | Daimler | [5 empty] | Alexandar
2019-03-22 | Daimler | [5 empty] | Keerthika
2019-03-23 | Ibill | deployment | 1 hours | completed | _ | form portal and disc | Hema
| Disc | Fix the bug and intergration | 4 hours | completed | _
| Forms portal | retro fitment form | 1 hours | completed | _
2019-03-25 | iStop | Date picker bug fixed | 1/2 hour | completed | - | Forms | S.Mayandi
| Disc | Fixed the bug ,Performance->ebse Integration, | 3 and 1/2 hours | completed | -
| Disc | PDP changes+PDP |  | In Progress | -
2019-03-26 | DISC | PMP , PDP , Deploy error - Bug fix | 8 hours | completed | - | iStop - Daimler deployment | Thenmozhi
2019-03-27 | Daimler | [5 empty] | Alexandar
2019-03-28 | Daimler | [5 empty] | Keerthika
2019-03-30 | iStop and Ispr | portal changes | 7 hours | completed | - | iStop | Hema
2019-04-02 | iStop | New changes fix | 3 hours | In Progress | - | Forms | Thenmozhi
| ISPR | New changes fix | 3 hours | Completed
2019-04-03 | iStop | changes fix | 3 hours | Completed | - |  | Keerthika
| ISPR |  | 3 hours
| Forms portal |  | 1hour
2019-04-04 | iStop | IE-11 compatibility | 7 hours | Completed | - | disc | hema
2019-04-05 | Disc | Performance, 2015-SRR, view, Integration | 2 hours | Completed | - | i-stop disc | Alexandar
|  | Performance,SRR KPI discussion with logesh | 2 hours | Completed
|  | user management packaging | 1/2 hours | Completed
| istop | Usb request | 1 hours | In Progress
2019-04-06 | istop | Bug Fix | 1 hour | completed | - | Disc | Mayandi
| ispr | Functionality fix | 1 hour
| istop | Usp Project Component | 2 hours
| Integration teaching | Teaching to alex | 2 hours | In Progress
2019-04-08 | Part details | Component creation | 4 hours | Completed | - | Daimler | Thenmozhi
| i-Stop | Bugs and changes | 4 hours | In Progress
2019-04-09 | Daimler | [5 empty] | keerthika
2019-04-15 | DISC | PDP and PMP bugs and changes | 8 hours | In Progress | - | PMP and PDP | Thenmozhi
2019-04-16 | DISC | PDP and PMP bugs and changes | 8 hours | In Progress | - | PMP and PDP | Hema
2019-04-17 | DISC | PDP and PMP bugs and changes | 8 hours | In Progress | - | PMP and PDP | keerthika
2019-04-19 | DISC | PDP and PMP bugs and changes | 4 hours | In Progress | - | PMP, PDP and Istop | Alexandar
| Istop | Change request page bug fix | 4 hours | completed | -
2019-04-20 | BusHr | Admin page design (UI) bug fix | 2.30 hours | completed | - | PMP, PDP and Istop | Mayandi
| PDP,PMP | Bug fix | 4 hours | In Progress
2019-04-24 | Daimler | [5 empty] | Thenmozhi
2019-04-25 | MES tracker | Bug fix | 4 hours | completed | - | Disc
| Packaging | Reassign option | 4 hours
2019-04-26 | disc portal | Bug fix | 4 hours | completed | - | Disc | Hema
| istop | Bug fix | 4 hours | completed
2019-04-27 | disc portal | Login security system | 8 hours | completed | - | disc portal | keerthika
2019-04-29 | i-Stop | Component Optimization | 8 hours | completed | - | disc portal | Alexandar
2019-04-30 | Disc | Component Optimization | 6 hours | In progress | - | PR | Mayandi
| istop | Bugs fix | 2 hours | completed
2019-05-02 | Disc | Process - Component Optimization | 4 hours | completed | - | iStop and DISC | Thenmozhi
| HRM, iTMS and iBill | Deployment | 2 hours | completed
| ISPR | API integration | 2 hours | completed
2019-05-03 | I-stop and Disc portal | API integration | 7hours | completed | - | Leave | Keerthika
2019-05-06 | Disc | people process component | 6 hours | completed | - | Disc | Mayandi
2019-05-07 | Disc | user management component | 7hours | completed | - | Daimler | Thenmozhi
2019-05-08 | Daimler | [5 empty] | Keerthika
2019-05-09 | Disc | Bug Fixing | 2hours | completed | - | Disc,I-stop | Aravin
| I-stop | High chart new version 7 issue resolved.Bug-fixing | 6hours | completed | -
2019-05-10 | i-stop | cio dashboard integration | 3hours | In Progress | - | cio dashboard IT support integration | Alexandar
| Disc | Bug Fixing | 2hours | completed | -
2019-05-11 | i-stop | cio dashboard integration and bug fixing | 6 hours | completed | - | Disc and i-Stop | Mayandi
| Disc | integration and bug fixing | 2 hours | completed
2019-05-13 | Disc | Packaging portal session integration | 3 hours | completed | - | Disc and i-Stop | Thenmozhi
| i-stop | cio dashboard integration | 5 hours | In Progress
2019-05-14 | i-Stop,Disc | bug fixing | 6 hours | completed | - | Daimler | Keerthika
| assesment | dynamic timer, view page | 2 hours | completed

## Alexandar
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
2019-03-19 | Forms | Submit form Modal | 2 hours | Complete | Laptop Slow | Finance form Validation | Thenmozhi
| Finanace form | Form Design | 2.5 hours | In Progress | Laptop Slow
| Integration learning | Learning | 1 hour | In Progress | -
2019-03-20 | Finance form | Validation | 6 hours | Complete | - | Remaining form design | Aravin
2019-03-21 | Finas ID Generation Forms | Preview method add | 2 hours | Complete | - | New Upload page design | Alexandar
| MES Showcase | Login and Main Page Design | 4 hours | Complete | -
|  | New Upload Page Design | 1 hours | In Progress | -
2019-03-22 | MES ShowCase | drag & drop fixed in upload pages | 6 hours | Complete | - | Forms correction and MES design correction | Keerthika
|  | and responsive fixed |  |  | -
2019-03-23 | MES Showcase | Index page | 7 hours | Complete | - | pdf viewer | Hema
2019-03-25 | MES PDF viewer | Learning | 7 hours | In Progress | - | pdf viewer | S.Mayandi
2019-03-26 | MES PDF viewer | Full screen Error fix | 7 hours | In Progress | - | Service Measure Portal | Thenmozhi
2019-03-27 | Service Measure Portal | Vehicle information Page | 6 hours | Complete | - | Service Measure Portal | Alexandar
|  | Component creation | 1 hour
2019-03-28 | Service Measure Portal | Part Information and cost information page | 2 hours | Complete | - | Service Measure Portal | Keerthika
2019-03-30 | Service Measure Portal | added the row and delete,learning the click event | 7 hours | In Progress | - | Service Measure Portal | Hema
2019-04-01 | Integration learning | List and add | 7 hours | In Progress | - | Integration learning | Mayandi
2019-04-02 | Integration learning | Edit and delete | 7 hours | In Progress | - | Integration learning | Thenmozhi
2019-04-05 | Integration learning | Nodejs file and API intergration | 6 hours | In Progress | - | Integration learning | Alexandar
| Service Measure Portal | Corrections | 1 hours | Complete | -
2019-04-06 | Service Measure Portal | corrections and pagination learning | 3 hours | Complete | - | Integration learning | Mayandi
| Integration learning | Integration learning through aravind and self learning | 3 hours | In Progress | -
2019-04-08 | Integration learning | ISPR intergration learning | 8 hours | In Progress | - | Integration learning | Thenmozhi
2019-04-09 | Integration learning | API Integration (edit, delete) | 8 hours | Complete | - | Integration learning | keerthika
2019-04-10 | Integration learning | API Integration (add,list,edit, delete) workout | 7 hours | Complete | - | Integration learning | Hema
2019-04-10 | ertino website | fom intergrate with keerthika | 1 hours | Complete | - |  | Hema
2019-04-11 | Integration learning | API Integration workout | 6 hours | Complete | - | Integration learning | Alexandar
|  | http service learning | 1 hours | Complete | - |  | Alexandar
2019-04-12 | Angular Materials | Collect the modules | 4 hours | In Progress | - | PMP | Mayandi
| Picture with content | Coding creation | 1 hour | Complete
| Integration teaching | Teaching to keerthi | 1 hour | Complete
2019-04-15 | PDP | Dashboard design changes | 2 hours | Complete | - | PMP, PDP and i-Stop | Thenmozhi
|  | APQP Planning page design changes | 1 hours
|  | PFEP Modal design changes | 2 hours
| Explanation | Integration code explanation | 1 hours
2019-04-16 | PDP | Dashboard design changes | 2 hours | Complete | - | Mez | hema
| MEZ | design changes | 3 hours | In Progress
| PFEP | corrections | 1 hours | complete
2019-04-17 | mes showcase | File upload design fixed (PDF,Images,Video) | 8hours | In Progress | - | mew showcase | Keerthika
2019-04-19 | mes showcase | File upload design fixed (PDF,Images,Video) | 8hours | Completed | - | Forms designing | Alexandar
2019-04-20 | MES showcase | File upload design fixed (PDF,Images,Video) preview | 3 Hours | Completed | - | Forms | Mayandi
| iStop | Dashboard Homepage Designing | 4 Hours
2019-04-24 | MES tracker | design changes | 4 Hours | Completed | - | MES tracker | Thenmozhi
MES showcase
2019-04-25 | MES tracker | design changes | 8hours | Completed | - | iStop
2019-04-26 | Mes tracker | design changes | 4 hours | Completed | - | - | Hema
| iStop-user | design | 4 hours | In Progress
2019-04-27 | Daimler-forms | design | 8hours | In Progress | - | will assigned by yogan | Keerthika
2019-04-29 | Daimler-forms | PMW request | 8hours | Completed | - | will assigned by yogan | Alexandar
2019-04-30 | Daimler-forms | Enable and disable file upload buttons | 4hours | Completed | - | Drag and drop file upload | Mayandi
|  | drag & drop file upload | 2 hours | In Progress
2019-05-02 | BUS HR | Single and Multiple Option fix | 4hours | Completed | - | Drag and drop functionality | Thenmozhi
|  | Drag and drop functionality | 4hours | In Progress
2019-05-03 | Daimler-forms | Fixed Drag and drop Functionality | 4hours | Completed | - | Time and Delay | keerthika
| Mes showcase | Time and Delay | 2hours | In Progress
2019-05-04 | I-stop-admin | Intergration | 3 hours | Completed | - | Time and Delay | Alexandar
| Daimler-forms | Vehicle information Page corrections | 2 hours | In Progress
| MES showcase | Time and Delay | 2 hours | In Progress
2019-05-06 | MES showcase | Time and Delay | 8 hours | Completed | - | will assigned by praba | Mayandi
2019-05-07 | Component creation | component creation for buttons,icons,animation,auto animation | 8 hours | Completed | - | will assigned by yogan | Thenmozhi
2019-05-08 | Chart | Chart Learning and Implementation | 8 hours | Completed | - | will assigned by yogan | Keerthika
2019-05-09 | I-Stop-User | Design Changes | 4hours | Completed | - | I-stop | Aravin
| Highchart | Learning | 4hours | Completed
2019-05-10 | I-Techquest | Home page design | 5 hours | Completed | - | I-Techquest | Alexandar
2019-05-11 | I-Techquest | exam instruction page design, morphing button full screen method and Review Questions page design | 7 hours | completed | - | I-Techquest | Mayandi
2019-05-13 | I-Techquest | Exam list page, Create exam page | 8 hours | completed | - | I-Techquest | Thenmozhi
2019-05-14 | I-Techquest | admin: upload exam page, categories page, technology page and bulk upload page designing | 7 hours | completed | - | I-Techquest | Keerthika

## Mayandi
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
19-03-2019 | Java Learning | Configuration Modal, Maven project creation | 6 hours | In progress | - | Java learning | Thenmozhi
2019-03-20 | Java Learning | Abstract, collections, maps,interface | 7 hours | In progress | - | Java learning | Aravin
2019-03-21 | Java Learning | Tables - Format cell content, Table Border, Adding Image, Tables list, Image rorate, scaling, Change position | 7 hours | In progress | - | Java learning | Alexandar
2019-03-22 | Java Learning | Java installation , PDF design - 20% | 6 hours | In progress | - | PDF design | Keerthika
2019-03-23 | Ispr | ispr pdf forms | 7 hours | In progress | - | PDF design | Hema
2019-03-25 | Ispr | ispr pdf forms | 7 hours | In progress | - | PDF design | S.Mayandi
2019-03-26 | Java Learning | Excel read,Write and Hypernet (ORM) learning | 7 hours | In progress | - | Hypernet learning | Thenmozhi
2019-03-27 | Java Learning | MVC - Spring - Created Rest API | 7 hours | In progress | - | MVC - Spring - Created Rest API | Alexandar
2019-03-28 | java learning | Spring - Rest controller | 7 hours | completed | - | Hypernet learning | Keerthika
2019-03-30 | java learning | hypernet-session factory,session transaction,collection mapping | 7 hours | completed | - | Hypernet learning | Hema
2019-04-01 | Java Learning | DAIMISPR MODEL PRACTICE | 7 hours | In progress | - | DAIMISPR MODEL PRACTICE | Mayandi
2019-04-02 | Java Learning | Learning spring framework annotations | 3 hours | completed | - | ISPR Coontroller | Thenmozhi
|  | ISPR Model , Configure | 3 hours | completed
|  | ISPR DAO | 1 hours | In progress
2019-04-03 | java learning | hypernet query language | 4 hours | In progress | - | hypernet query language | Keerthika
|  | DaIMISPR MODEL creation | 3 hours | In progress
2019-04-04 | java learning | Daim-ISPR model-save | 5 hours | completed | - | hypernet query language and mapping | Hema
|  | Daim-ISPR model-list | 2 hours | In progress
2019-04-05 | Java Learning | MS SQL data fetching | 4 hours | In progress | - | Spring | Alexandar
|  | MS SQL installation | 3 hours | completed | Installaiton issue
2019-04-06 | PDF iText | Data fetch from mssql to used PDF with JDBC and alignment | 4 hours | completed | - | Hypernet learning | Mayandi
| Java Learning | MSSQL changed windows authentication to server authentication | 1 hours | completed
|  | Hibernate config and Pdf | 2 hours | In progress
2019-04-08 | Spring | Generating PDF | 3 hours | In progress | - | Hypernet learning | Thenmozhi
| Hypernate | DB configuration | 4 hours | completed
2019-04-09 | Spring | Generating PDF | 7hours | In progress | - | spring learning | Keerthika
2019-04-10 | Spring | Generating PDF | 7hours | In progress | - | spring learning | Hema
2019-04-11 | Java Learning | stack and Heap | 7hours | completed | - | spring learning | Alexandar
2019-04-12 | Spring | Dynamic pdf create | 5 hours | completed | - | spring learning | Mayandi
| Spring learning | Data fetch from mssql to used PDF | 3 hours | In progress
2019-04-15 | Learning | MS SQL | 2 hours | In progress | - | Hypernate | Thenmozhi
| Hypernate | Mapping Learning 1 to many, many to 1 | 3 hours
| ISPR | 8 D Details | 2 hours
2019-04-16 | PDF | Generating PDF | 7 hours | completed | - | - | Hema
2019-04-17 | Spring | Create Excel sheet | 8hours | completed | - | spring learning | Keerthika
2019-04-19 | Spring | Excel learning | 3hours | completed | - | Image upload | Alexandar
| Assign ISPR | Bug fixed | 4hours | completed
| ISPR | Image upload bug | 1hour | In progress
2019-04-20 | ISPR | Image upload bug | 6 hours | completed | - | Excel Generator | Mayandi
2019-04-24 | DISC | PSW PDF | 8 hours | completed | - | PSW PDF | Thenmozhi
2019-04-25 | DISC | PSW PDF | 4hours | completed | - | Attendance excel sheet
| Attendance | Excel sheet creation | 4hours | completed | -
2019-04-26 | Attendance | Attendance time | 4hours | completed | - | - | Hema
| DISC | PSW PDF | 4hours | completed
2019-04-27 | mail | Automatic mail and mongo db learning | 8 hours | completed | - | mongo db | Keerthika
2019-04-29 | mail | Added sevael logo with signature | 8 hours | completed | - | mongo db | Alexandar
| mongo db | Create db, collections and field |  | In progress
2019-04-30 | mongo db | Aggregate, java | 8 hours | In progress | - | mongo db | Mayandi
2019-05-02 | mongo db | Aggregate, java | 8 hours | In progress | - | mongo db | Thenmozhi
2019-05-03 | GitLab | Working GitLab with Eclipse | 6 hours | completed | - | Time Management | keerthika
2019-05-04 | System changing | System changing | 3 hours | - | - | iTMS | Alexandar
| iTMS | Learning | 5 hours | In progress
2019-05-06 | iTMS | Learning | 8 hours | In progress | - | iTMS | Mayandi
2019-05-07 | iTMS | Learning | 6 hours | In progress | - | itechquest | Thenmozhi
| itechquest | Learning | 2 hours | In progress | -
2019-05-08 | itechquest | Learning | 8 hours | In progress | - | itechquest | keerthika
2019-05-09 | iTMS | Bug-Fixing(Only login page) | 2 hours | completed | - | itechquest | Aravin
| itechquest | Learning | 6 hours | In progress | -
2019-05-10 | itechquest | Learning | 5 hours | completed | - | itechquest | Alexandar
2019-05-11 | iTMS | excelUpload | 5 hours | In progress | - | itechquest | Mayandi
| itechquest | learning | 2 hours | In progress
2019-05-13 | itechquest | API learning | 5 hours | In progress | - | itechquest | Thenmozhi
| Attendance | Weekly report Email issue | 3 hours | completed
2019-05-14 | itechquest | Learning | 3 hours | In progress | - | itechquest, iTMS | Keerthika
| sevael weekly Attendance email | Bug fixing | 1 hour | completed
| iTMS | Excel upload | 3 hours | In progress

## Keerthika
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
19-03-2019 | Component creation | Check box creation | 2 hours | In Progress | - | Bus ISFM portal | Thenmozhi
| iStop | Responsive screens | 3 hours | Completed
| PMP | Dashboard changes | 1 hours | Completed
2019-03-20 | Boostrap 4 | learning | 2 hours | In Progress | - | ESFM - POC | Aravin
| DISC | Bug fix | 3 hours | Completed
| Aatralz | Helping hema | 30 mins | Completed
| PR | Masters page | 30 mins | Completed
2019-03-21 | Aatralz | Skill block page | 4 hours | Completed | - | Istop | Alexandar
| iStop | KT from Vijay kumar | 1 hours | Completed
2019-03-22 | iStop | Learning API Integration and Sidebar Fixed | 6 hours | In Progress | - | Will assign by Vijayakumar | Keerthika
2019-03-23 | Component creation | creation html,css and js files | 1 hours | Completed | - | bus hr | Hema
| iStop | intergration | 3 1/2 hours | Completed
| iStop | fix the bug ui | 2 hours | In Progress
2019-03-25 | iStop | Bug fixed | 3Hours | Completed | - | Ertino | S.Mayandi
| Bus Hr | Login page,Course list page, model page | 4 hours
2019-03-26 | Ertino - website | Ertino website in Wordpress | 4 hours | - | - | Ertino website in HTML | Thenmozhi
|  | Ertino website in HTML | 4 hours | In Progress
2019-03-27 | Ertino - website | Ertino website in HTML | 5 hours | In Progress | - | Ertino website in HTML | Alexandar
| Component module | Module creation for Alexander | 1 hours | Completed
2019-03-28 | Bus-hr | designed course list page and responsive fix | 7 hours | Completed | - | Will assign by Yogan | Keerthika
2019-03-30 | Bus-hr | create a modules and pages | 6 hours | Completed | - | will assign by Yogan | hema
2019-04-01 | Bus-hr | Modules import | 1 1/2 hours | Completed | - | sevael website | Mayandi
| Drupal | Theme create | 4 hours | Completed
| Sevael | Home page | 2 1/2 hours | In Progress
2019-04-02 | Sevael website | Home page, Application development page, Application maintence support page, Legacy modulation page, Cloud comsulting page | 8 hours | Completed | - | Sevael website | Thenmozhi
2019-04-03 | Sevael website | Managed services page,mobile application page,automation page | 8 hours | Completed | - | Sevael website | Keerthika
2019-04-04 | Sevael website | set with carousel , navbar and responsive the pages | 8 hours | Completed | - | Will assign by Yogan | Keerthika
2019-04-05 | Sevael website | set with responsive the pages and footer | 5 hours | In Progress | - | Bus-hr-admin | Alexandar
| Bus-hr-admin | correction | 2 hours | In Progress
2019-04-06 | Bus-hr-user | correction | 5 hours | Completed | - |  | Mayandi
| Ertino - website | Website in html | 2 and 1/2 hours | In Progress
2019-04-08 | Bus-hr-user | Design changes | 5 hours | In Progress | - | Bus-hr-admin | Thenmozhi
| Bus-hr-admin | Dynamic List and pagination | 3 hours | Completed
2019-04-09 | Bus-hr | Design correction | 7hrs | Completed | - | Will assign by Yogan | Keerthika
Ertino - website
| API Integration Learning | List and add | 1hrs | In Progress
2019-04-10 | Ertino - website | about us and carrer design and form intergrate | 8 hours | In Progress | - | Ertino - website | Hema
2019-04-11 | Ertino - website | contact form mail funtion in php | 8 hours | Completed | - | Ertino - website | Alexandar
2019-04-12 | CRUD Learning | create and read learning | 7 hours | completed | - |  | Mayandi
2019-04-15 | Component creation | Importing Modules | 1 hour | Completed | - | CR Portal design | Thenmozhi
| i-Stop | Bug Fix | 1 hour | Completed
| Ertino | Converting HTML to Wordpress | 3 hours | In Progress
| CR Portal | Design | 2 hours | In Progress
2019-04-16 | CR Portal | Design | 7 hours | Completed | - | Istop | Hema
2019-04-17 | iStop | Change Request design changes | 4hours | Completed | - | Mes tracker | Keerthika
| Mes tracker | Designed the Mestracker | 4hours | In Progress
2019-04-19 | Mes tracker | HDT BS, MEPT | 7hours | Completed | - |  | Alexandar
| iStop | Vendor Portal | 1hours | In Progress
2019-04-20 | iStop | Vendor Portal | 4 hours | Completed | - |  | Mayandi
| BusHr | User correction | 3 hours | In Progress
2019-04-24 | Mes tracker | Design | 4 hours | Completed | - | Mes tracker | Thenmozhi
| Forms | Design | 4 hours | Completed
2019-04-25 | Mes tracker | Design | 4 hours | Completed | - | iStop
| iStop | Design | 4 hours | Completed
2019-04-26 | Mes tracker | design changes | 2 hours | Completed | - | - | hema
| iStop-user | design | 3 hours
| pr-portal | design | 3 hours
2019-04-27 | iStop-user | design changes | 8 hours | Completed | - | will assigned by yogan | keerthika
2019-04-29 | iStop-user | design changes | 8 hours | In Progress | - | will assigned by yogan | Alexandar
2019-04-30 | iStop-user | animation | 8 hours | In Progress | - |  | Mayandi
| iStop-admin | IT announcement
2019-05-02 | IT annoucement | design changes | 4 hours | Completed | - | will assigned by yogan | Thenmozhi
| istop - PR | design changes | 2 hours | Completed | -
| Invoicing | design changes | 2 hours | Completed | -
2019-05-03 | iStop-user | Fixed Mobile Responsive | 6 hours | Completed | - | will assigned by yogan | Keerthika
| components | Create components |  | In Progress
2019-05-04 | iStop-admin | Invouces intergratation,design corrections | 7 hours | Completed | - | will assigned by yogan | Alexandar
2019-05-06 | iStop - admin, Bus Hr user | change the search box design, Design correction | 1 hour | completed | - | iStop | Mayandi
| Mes tracker | Design changes & correction | 6 hours
2019-05-07 | Mes tracker | Design changes & correction | 4 hours | completed | - | CIO Dashboard | Thenmozhi
| i-Stop | CIO Dashboard | 3 hours
2019-05-08 | iStop-admin | CIO Dashboard | 7 hours | In Progress | - | CIO Dashboard | Keerthika
2019-05-09 | iStop-admin | CIO Dashboard | 3 hours | completed | - | CIO Dashboard | Aravin
|  | IT-Support | 4 hours | completed | - | I-stop
2019-05-10 | iStop-admin | CIO Dashboard | 3 hours | completed | - | CIO Dashboard | Alexandar
| i-techquest | Exam Instructions | 3Hours | In Progress | - | i-techquest
2019-05-11 | i-techquest | Exam screen page design and functionalites | 6 hours | In Progress | - | i-techquest | Mayandi
| i-techquest | Model function | 1 hour | Completed
2019-05-13 | i-techquest | User page design | 3 hours | Completed | - | Will assign by Yogan | Thenmozhi
| istop - user | Self help solutions page changes | 4 hours | In Progress
2019-05-14 | istop - user | know more functionality | 3 hours | Completed | - | istop website | Keerthika
| assesment - user | next previous functionality | 4 hours
| skilguru - user | Learning | 1 hours

## Thenmozhi
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
19-03-2019 | DISC | PMP Test plan documentation | 3 hours | Completed | - | PR Documentation | Thenmozhi
|  | PDP Test plan documentation | 2 hours | Completed | -
|  | ISPR Test plan documentation | 1 hours | In Progress | -
|  | BUGS | 1 hours | In Progress | -
2019-03-20 | DISC | ISPR Test plan documentation | 3 hours | Completed | - | PR Documentation | Aravin
|  | BUGS | 1 hours | Completed | -
| PR | Test plan Documentation | 4 hours | In Progress | -
2019-03-21 | PR | Test plan Documentation | 7 hours | In Progress | - | Disc user manual | Alexandar
2019-03-22 | PR | Test plan Documentation | 5 hours | Completed | - | Disc user manual | Keerthika
| DISC Bugs | Discussed with aravin and verified the pending bugs | 1 hours | Completed | -
2019-03-23 | Pr | documentation changes | 2 hours | In Progress | _ | pr and disc | Hema
| Disc | user manual | 1 hours | In Progress
| istop,pdp,ertino | fix the ebug | 4 hours | In Progress
2019-03-25 | Disc | Supplier login issue | 1 hour | Completed | - | Disc | S.Mayandi
|  | Testing process, PDP,PMP | 5hours | Completed
|  | Meeting with Rajkumar | 1hour | Completed
2019-03-26 | DISC | PDP and PMP Bugs reporting | 8hours | In Progress | - | iStop | Thenmozhi
2019-03-27 | i-Stop | i-Stop bugs reporting | 7hours | In Progress | - | iStop | Alexandar
| Disc Portal | Explanation given to SATHEESH about User previleges and Process module for user documentation | 1hours | Completed
2019-03-28 | Ertino | Ertino bug discussion with vijay | 5hours | Completed | - | iStop | Keerthika
| Packaging portal | File upload issue | 2hours | Completed
2019-03-30 | Disc Portal | use management documentataion | 8 hours | In Progress | - | iStop,ispr | Hema
2019-04-01 | Disc and Package | Update bug tracker, user mnual documentaion | 6 hours | Completed | - | ISPR Testing | Mayandi
| iStop | Testing process | 1 hour | Completed
2019-04-02 | DISC | User Manual documentation | 2 hour | In Progress | - | DISC | Thenmozhi
| Ertino | Rest API Documentation | 2 hour | In Progress | - | Ertino
| ISPR and i-Stop | Issue tracker updation | 3 hours | Completed | - | ISPR and i-Stop
| Ertino | BUGS | 1 hours | In Progress | - | Ertino
2019-04-03 | ISPR,ISTOP and Ertino | BUGS | 6hours | In Progress | - | Istop,ISPR and Ertino | Keerthika
| Ertino | Rest API Documentation Ertino | 1 hours
2019-04-04 | ISPR and ISTOP | bugs | 2 hours | Completed | - | Rest Api and Disk Manaual Documentation | Hema
| Daimler | Meeting with Srinee | 2 hours | Completed
| Disk manaual | bugs | 3 hours | In Progress
2019-04-05 | Ertino | Testing | 1 hour | In Progress | - | Ertino | Alexandar
| Disc | Discussion with client | 5 hours | Completed
| Ertino | Documentation Rest API | 2 hour | In Progress
2019-04-06 | ispr, istop | Bugs | 2 hours | Completed | - | Disc | Mayandi
| Ertino |  | 5 hours
|  | Rest api documentation | 1 hour
2019-04-08 | Disc | Part and supplier mapping data | 4 hours | Completed | - | i-Stop | Thenmozhi
|  | User manual documentation | 1.5 hours | In Progress
| i-Stop | Bugs | 3 hours | Completed
2019-04-09 | Ertino | Bugs Verification | 8hours | In Progress | - | Disc | keerthika
| Disc | Disc Portal issues
2019-04-11 | Packaging | Packaging documents | 3hours | Completed | - | PMP, Daimler meeting with client | Alexandar
| Report | Mobile app testing | 1hour
| Disc | Part mapping | 4hours
2019-04-12 | Discussion with daimler client | PDP, PMP. | 6 hours | Completed | - |  | Mayandi
|  | UAT TESTING | 2 hours | Completed | -
2019-04-15 | i-Stop | Bugs | 1 hour | Completed | - | PDP , PMP , i-stop and Ertino | Thenmozhi
| Ertino | Bugs Verification | 3 hours | In Progress
| PDP and PMP | Bugs and Changes initmating | 3 hours | In Progress
2019-04-16 | PDP and PMP | Bugs and Changes initmating | 7 hours | In Progress | - | PDP and PMP | hema
2019-04-17 | PDP and PMP | Bugs | 7 hours | In Progress | - | PDP and PMP | Keerthika
2019-04-19 | ISTOP | CR Bug | 2hours | Completed | - | PDP and PMP | Alexandar
| Disc | PMP and PDP | 5hours | In Progress
2019-04-20 | PDP and PMP | Bugs intimating | 8 hours | In Progress | - | PDP and PMP | Mayandi
2019-04-24 | Daimler | [5 empty] | Thenmozhi
2019-04-25 | Packaging | Bugs | 8 hours | Completed | - | DISC
DISC
2019-04-26 | PDP and PMP | bugs | 8 hours | Completed | - | Disc portal and process video documentation | Hema
Disc Portal
2019-04-27 | Disc Portal | Disc portal and process video documentation | 8 hours | In Progress | - | Disc portal and process video documentation | keerthika
2019-04-29 | Disc | Documentation | 8 hours | Completed | - | Documentation | Alexandar
2019-04-30 | Disc | Documentation | 2 hours | In Progress | - | Documentation | Mayandi
| Report | Mobile app testing | 6 hours | In Progress
2019-05-02 | Report | Mobile app testing | 2 hours | In Progress | - | iTMS and HRM | Thenmozhi
| iTMS and HRM | Bugs | 4 hours | In Progress
| Ertino | Bugs Verification | 2 hours | In Progress
2019-05-03 | Ertino | Bugs Verification | 8 hours | Completed | - | disc portal | Keerthika
| invoicing | Bugs Verification
| Itms | Portal Explaination and meeting
2019-05-04 | Disc | Testing, | 2 hours | Completed | - | Documentation | Alexandar
|  | created doumentation, KT | 3 hours | In Progress
| Report App | Report App Testing | 3 hours | In Progress
| I-Stop | Invoices Testing | 1 hour | Completed
2019-05-06 | Disc | User document | 6 hours | completed | - | Disc | Mayandi
| Ertino | documents | 1 hour | completed
2019-05-07 | Report App | Report App Testing | 4 hours | completed | - | Documentation | Thenmozhi
| Disc | User document | 4 hours | completed
2019-05-08 | Disc | documents | 8 hours | completed | - | Documentation | Keerthika
2019-05-09 | MOBILE-APP | SRR Report | 4 hours | In-progress | - | Documentation | Aravin
| Disc | PDP,PMP | 4 hours | In-progress | -
2019-05-10 | MOBILE-APP | SRR Report | 3 hours | In-progress | - | Documentation | Alexandar
| Disc | PDP,PMP | 3 hours
2019-05-11 | Disc | User manual | 5 hours | In Progress | - | KT, User documentation | Mayandi
| Disc | KT to satheesh | 2 hours | In Progress
| Ertino | Bug | 1 hours | In Progress
2019-05-13 | Disc | KT to satheesh | 5 hours | Completed | - | Leave | Thenmozhi
|  | Bugs | 2 hours | In Progress

## Manikandan
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
2019-04-12 | IBMS | React Native | 5 hours | In progress | - | React Native, Ibms(Daimler) | Mayandi
|  | iBMS(Daimler) | 2 1/2 hours | In progress
| Sevael - Visitor log | Visitors Log | 20 minutes | Completed
2019-04-15 | Report | React native - Login screen and navigation design | 8 hours | Completed | - | Report mob app | Thenmozhi
2019-04-16 | Report | React native - Login screen and navigation design,splash screen and login type and timer intergration | 7 hours | Completed | - | landing screen | hema
2019-04-17 | Reactnative | Navigation Drawer | 8 hours | Completed | - |  | keerthika
2019-04-19 | Reactnative | Navigation Drawer Progress Implementation | 8 hours | In progress | - | Navigation Drawer Implementation | Alexandar
2019-04-20 | Reactnative | Navigation Drawer Progress Implementation | 8 hours | In progress | - | Navigation Drawer Implementation | Mayandi
2019-04-24 | Reactnative | Tab view , Tool bar and list view creation | 8 hours | 8 hours | - | View pager creation | Thenmozhi
2019-04-25 | Reactnative | View pager , Section list | 8 hours | Completed | - | React native components
2019-04-20 | Reactnative | Stored data in local and set with date and time picker | 8 hours | Completed | - | API | hema
2019-04-27 | API Integration | API Integration and Post method implementation | 8 hours | In progress | - | API | keerthika
2019-04-29 | Reactnative | Camera access and File access | 8 hours | In progress | - | Reactnative | Alexandar
2019-04-30 | Reactnative | Camera access and File access | 7 hours | In progress | - | Reactnative | Mayandi
2019-05-03 | Reactnative | Animation | 6hours | Completed | - | API | keerthika
2019-05-04 | Report App | Exploring coding in report | 7 hours | Completed | - | will assigned by yogan | Alexandar
2019-05-06 | Template | Login signup | 7 hours | completed | - | will assigned by yogan | mayandi
2019-05-07 | Skillguruu | pie version update | 5 hours | completed | - | UI for skillguruu | Thenmozhi
| Reactnative | Buttons | 2 hours | completed | -
2019-05-08 | Reactnative | chart design implementation | 8 hours | completed | - | will assigned by yogan | keerthika
2019-05-09 | Reactnative | High chart design implementation And Api Integration with live data. | 8 hours | completed | - | will assigned by yogan | ARAVIN
2019-05-10 | Reactnative | Api Integration with live data in chart | 4 hours | In progress | - | will assigned by yogan | Alexandar
2019-05-11 | Reactnative | Api Integration with live data in chart | 7 hours | In progress | - | will assigned by yogan | Mayandi

## Tamilselvan
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
2019-05-13 | Learning | HTML Forms, New element, migration , graphics, Canvas, SVG | 8 hours | Inprogress | - | HTML Learning | Thenmozhi
2019-05-14 | Learning | HTML and css topic:list ,tables,overflow,position,float,align | 8 hours | Inprogress | - | CSS Learning | Keerthika

## Aravindhan
Project Plan & Status
Date | Project | Task Assigned | Duration | Status | Remarks | Plan for tomorrow | Status Responsible Person
2019-05-13 | Learning | HTML Elements, heading,styles,formatting,quotation,commands,colour,image | 8 hours | Inprogress | - | HTML Learning | Thenmozhi
2019-05-14 | Learning | html5,html graphics,html media and the basics of css like introduction,borders and colors etc..And learned the linking of css file with html. | 8 hours | Inprogress | - | HTML Learning and CSS | Keerthika